## Sheet1
Kanen Online Shopping | Taks List
User Stories |  |  | Mandays
Maintain cart upon logout
T001 | On logout there should be a prompt to Either save his cart or clear it once he leave | Aica Flores
| The Cart Display should be cleared once he logs out. But should save to db if he chooses yes in the prompt | Aica Flores
| Need the whole cart store and the user id to save the cart in the DB | Aica Flores
T002 | Once he logs in again and if he has a saved transaction it will have a prompt if he wants to continue the cart or new cart | Aica Flores
T003 | Updating the quantity of the item in the cart. | Aica Flores
Conversion of JDBC to JPA
T004 | Changing the models to Entity so we can use JPA | JB Vergara
T005 | Revamping the DAO’s and Services(IMPL) for the usage of the entities | JB Vergara
T006 | Usage of Transactional Block for the insert of the Order & Order Items while also using the JPA | JB Vergara
T007 | Updating some controllers to be use as webservices in retrieving JSON data from the DB | JB Vergara
User Profile
T008 | Transaction page will be converted to the Profile page | Alexis Cuntapay
| View & Updating of User Profile like email, mobile, address, password & etc. | Alexis Cuntapay
| Still shows Previous Transactions | Alexis Cuntapay
T009 | Request for discount Level (JMS Producer) | Alexis Cuntapay
Admin Application
T010 | Receive Request of JMS Producer & Save to DB | CJ Kanen
T011 | Show All Request to be approve | CJ Kanen
T012 | Update The status of a Order | CJ Kanen
T012 | View all the Orders | CJ Kanen
Backend application
T010 | Receive Request of JMS Producer & Save to DB | Melvin Yu
T011 | Show All Request to be approve | Melvin Yu
T012 | Update The status of a Order | Melvin Yu
T012 | View all the Orders | Melvin Yu
Documentation
T013 | Usecase Diagram | Sebastian Briones
T014 | ERD | Sebastian Briones