## Sheet1
Initial Plan |  | Estimate | Actual time | Status
JB
Customers can add their favorite items to their cart and pay for them | new window with grid | 3 hours |  | for integration in 3 hrs
| update db with new table | 15 mins | 3 hrs total | done
| update ERD | 15 mins |  | done
| update cart controller | 45 mins |  | done
| service | 30 mins |  | done
| DAOImpl | 30 mins |  | done
Aica
Customers can give a comment of the product | Update db, assn table between user and product |  |  | done
| UI pop up window | 2 hours |  | done
| Update Product Controller | 1hr | 1.25 hrs | done
| Product Service | 30 mins |  | done
| DAOImpl | 30 mins | 1 hr | done
Baste
Search the products | clear display, recreate from store | 1hr | 2.5hr
Fix approved membership request | fix JPA | 3 hrs | resolved by Teacher Mike (5 mins) | done
UI Design, icons | Me |  |  | done
Melvin
Manage Users (Including blacklisting of users) | UI form | 3 hours
| User Controller | 30 mins | 2.5 hrs total
| User Service | 30 mins
| UserDAOImpl | 30 mins
Alexis
See details of a product | UI Form | 2 hrs | 2 hrs | done
check count of logged in users in admin (dynamic filter) | Java | 3 hrs
log 4j by size | Java | 2 hrs
Kanen
PRODUCTS CRUD on admin side | UI Panel | 2 hours
| Add Product UI |  | 1.25 | done
| Update product |  | 1.25 | done
| Product Controller | 1 hour | 1 hour | ready for testing in UI
| Product Service | 1 hour | 1 hour | ready for testing in UI
| DAOImpl | 1 hour | 1 hour | ready for testing in UI
JUnitTestCase for add product
JUnitTestCase for update